## Product Backlog
ID | User Story
1 | As a user I should be able to login to my portal
2 | As a student/advising I should view my personal schedule and all groups schedules and to be able to switch my group with other students
3 | As a staff member I should be able to view my working hour schedule and session timings
4 | As a staff member I should be able to view my proctoring schedule and switch with available teachers/timings
5 | As a staff member I sould be able to enter/modify students grades including coursework,quizzes,bonus,final,midterms
6 | As a staff member I should be able to view students grades and view statistical charts for results
7 | As a staff member I should be able to enter/modify attendance for students
8 | As a staff member I should be able send mails to my students
9 | As a student I should be able to view my grades for each subject including coursework and exams
10 | As a student I should be able to apply for internship and submit internship certificates
11 | As a student I should be able to choose my major and choose engineering seminars
12 | As a student I should be able to apply for major/elective courses
13 | As a student I should be able to apply for makeup and imporvement exams and remarking forms
14 | As a student I should be able to view my exams schedules with corresponding timing and locations
15 | As a student I should be able to view my financial balance and deadline for payements
16 | As a staff member I should be able to reserve a room/hall for teaching
17 | As a student I should be able to reserve a study room or a pitch or locker on campus
18 | As a proffessor I should have a researcher portal view my masters/PHD students and their corresponding work/thesis so far divided into currently studenting or finalized
19 | Have an interactive student/staff platfrom including forums for posting helpful questions
20 | As a student/TA I should be able to upload my masters/bachelor thesis
21 | As a student I should have a platfrom to post my complains or problems in case of lost id or problem regarding a studied course
22 | As a student I should be able to evaluate courses respectively
23 | As a staff member I should be able to view evaluations answered by my students
Each persona is highlighted in a different Colour

## Sprint Backlog
ID | User Story | TASKS | Team Member | Story points | Reason
1 | As a user I should be able to login to my portal | login with name and password | Ahmed Ossama | 4 | it requires dealing with user inputs
|  | check for correct info entered | Nourhan Salah | 6 | it requires configuration of data and test case
2 | As a student/advising I should view my personal schedule and all groups schedules and to be able to switch my group with other students | view all groups schedule | Omar Ads | 6 | it requires dealing with tabling and viewing data from database
|  | view personal student schedule | Samar Shokry | 6 | it requires dealing with tabling and find specified data in database according to inputs and paramaters
|  | view matching students schedules | Aly Elshamy | 6 | it requires dealing with inputs and saving these inputs into permenent files in database
|  | apply/respond for switching requests | Aly Elshamy | 6 | it requires dealing with getting specific data from database and viewing them
3 | As a staff member I should be able to view my working hour schedule and session timings | view all groups schedule | Omar Ads | 3 | it requires dealing with tabling and viewing data from database
|  | view personal session hours schedule | Samar Shokry | 3 | it requires dealing with tabling and find specified data in database according to inputs and paramaters
4 | As a staff member I should be able to view my proctoring schedule and switch with available teachers/timings | view personal proctoring schedule | Samar Shokry | 3 | it requires dealing with tabling and find specified data in database according to inputs and paramaters
|  | apply/respond for proctoring switch requests | Ahmed Ossama | 3 | it requires taking and saving request as well as sending notifications for destinations
5 | As a staff member I sould be able to enter/modify students grades including coursework,quizzes,bonus,final,midterms | view specific tutorial students | Samar Shokry | 6 | it requires dealing with tabling and find specified data in database according to inputs and paramaters
|  | enter/modify student grade accordingly | Ahmed Ossama | 6 | it requires taking crucial inputs and saving them into databse accordingly
6 | As a staff member I should be able to view students grades and view statistical charts for results | lookup a student name from dropdown list | Nourhan Salah | 3 | it requires a view for choosing data as well as tables to choose items from
|  | view charts/histograms for student | Nourhan Salah | 3 | it requires applying charts and graphs of data retrieved from database accordingly
|  | view specific student grades | Omar Ads | 3 | it requires dealing with tabling and find specified data in database according to inputs and paramaters
7 | As a staff member I should be able to enter/modify attendance for students | view specific member teaching tutorials list | Omar Ads | 3 | it requires dealing with tabling and find specified data in database according to inputs and paramaters
|  | enter/modify attendance for each student | Aly Elshamy | 3 | it requires taking input and updating database accordingly
8 | As a staff member I should be able send mails to my students | Write emails | Aly Elshamy | 3 | it requires taking input as well as verifiying acceptability in place
|  | select and send email to recievers | Ahmed Ossama | 3 | it requires choosing selection from a list of options retrieved from database accordingly
9 | As a student I should be able to view my grades for each subject including coursework and exams | view personal grades | Samar Shokry | 3 | it requires dealing with tabling and find specified data in database according to inputs and paramaters
|  | view cummilative transcipt for all years | Samar Shokry | 3 | it requires dealing with tabling and find specified data in database according to inputs and paramaters
10 | As a student I should be able to apply for internship and submit internship certificates | view students internship status and upload ceritficates | Nourhan Salah | 2 | it requires with retrieving specific data from database and uploading sheets back to the system
11 | As a student I should be able to choose my major and choose engineering seminars | Register student in major/seminar | Ahmed Ossama | 2 | it requires taking input and updating database accordingly
12 | As a student I should be able to apply for major courses | Apply for course from list of available courses | Aly Elshamy | 1 | it requires taking input and updating database accordingly
13 | As a student I should be able to apply for makeup and imporvement exams | Apply for available makeup exams and imporvements | Aly Elshamy | 2 | it requires taking input and updating database accordingly
14 | As a student I should be able to view my exams schedules with corresponding timing and locations | view personal exam schedule | Samar Shokry | 2 | it requires dealing with tabling and find specified data in database according to inputs and paramaters
15 | As a student I should be able to view my financial balance and deadline for payements | view personal schedule for deadlines of upcoming payements | Samar Shokry | 2 | it requires dealing with tabling and find specified data in database according to inputs and paramaters
16 | As a staff member I should be able to reserve a room/hall for teaching | view list of available rooms/halls in specified timing and mark as reserved | Omar Ads | 1 | it requires dealing with tabling and find specified data in database according to inputs and paramaters
17 | As a student I should be able to reserve a study room or a pitch or locker on campus | view list of available study rooms and pitches in specified timing and mark as resereved | Omar Ads | 1 | it requires dealing with tabling and find specified data in database according to inputs and paramaters
18 | As a proffessor I should have a researcher portal view my masters/PHD students and their corresponding work/thesis so far divided into currently studenting or finalized | check students status and progress | Samar Shokry | 4 | it requires retrieving specific data from database and viewing them in tables
|  | enter their grades/ any amendments required | Ahmed Ossama | 4 | it requires taking crucial inputs and saving them into databse accordingly
19 | Have an interactive student/staff platfrom including forums for posting helpful questions | view all previous questions | Omar Ads | 4 | it requires dealing with tabling and find specified data in database according to inputs and paramaters
|  | post/answer questions | Nourhan Salah | 4 | it requires taking input as well as verifiying acceptability in place and notifying the system
20 | As a student/TA I should be able to upload my masters/bachelor thesis | Upload masters/thesis portal | Aly Elshamy | 3 | it requires taking uploads from user and updating databases
21 | As a student I should have a platfrom to post my complains or problems in case of lost id or problem regarding a studied course | report/post problems to board | Nourhan Salah | 4 | it requires taking input as well as verifiying acceptability in place and notifying the system
22 | As a student I should be able to evaluate courses respectively | Upload evaluation results | Aly Elshamy | 3 | it requires taking input from user and updating databases
23 | As a staff member I should be able to view evaluations answered by my students | View Evaluations | Samar Shokry | 2 | it requires retrieving specific data from database and viewing them in tables
each sprint is highlighted in a different color

## Sprint 1
SPRINT 1 DETAILED BACKLOG
TASK | TEAM MEMBER | STORY POINTS | REASON
login with name and password | Ahmed Ossama | 4 | it requires dealing with user inputs
check for correct info entered | Nourhan Salah | 6 | it requires configuration of data and test case
view all groups schedule | Omar Ads | 6 | it requires dealing with tabling and viewing data from database
view personal student schedule | Samar Shokry | 6 | it requires dealing with tabling and find specified data in database according to inputs and paramaters
view matching students schedules | Aly Elshamy | 6 | it requires dealing with inputs and saving these inputs into permenent files in database
apply/respond for switching requests | Aly Elshamy | 6 | it requires dealing with getting specific data from database and viewing them
view all groups schedule | Omar Ads | 3 | it requires dealing with tabling and viewing data from database
view personal session hours schedule | Samar Shokry | 3 | it requires dealing with tabling and find specified data in database according to inputs and paramaters
view personal proctoring schedule | Samar Shokry | 3 | it requires dealing with tabling and find specified data in database according to inputs and paramaters
apply/respond for proctoring switch requests | Ahmed Ossama | 3 | it requires taking and saving request as well as sending notifications for destinations

## team info
NAMES | ID
Ahmed Ossama | 43-823 | ahmed2ossama@gmail.com>
Aly Elshamy | 43-5520 | elshamyali19@gmail.com
Nourhan Salah | 43-5139 | nourhan.salah1@hotmail.com
Omar Ads | 43-12699 | omarsalaheldinads@gmail.com
Samar Shokry | 43-1746 | samoshokry@gmail.com